## Dashboard
PROGRAM EVALUATION TOOLKIT
Program Evaluation and Impact Measurement
PROGRAM INFORMATION
Program Name: |  | Program Director:
Start Date: |  | End Date:
Target Population: |  | Annual Budget:
EVALUATION STATUS
Component | Status | Completion % | Notes
Logic Model | Complete | 100% | Approved by stakeholders
Evaluation Plan | In Progress | 75% | Finalizing data collection methods
Data Collection Tools | In Progress | 50% | Survey designed, testing needed
Baseline Data | Not Started | 0% | Scheduled for next month
Outcomes Tracking | Not Started | 0% | Awaiting baseline data
Impact Report | Not Started | 0% | Due at program end
KEY METRICS SUMMARY
Metric | Target | Current | % of Target
Participants Served | 500 | 342 | 68%
Program Completion Rate | 80% | 85% | 106%
Participant Satisfaction | 4.0/5.0 | 4.3/5.0 | 108%
Knowledge Gain (pre-post) | 20% | 28% | 140%
QUICK ACTIONS
1. Complete Logic Model and get stakeholder approval
2. Finalize Evaluation Plan with timeline and budget
3. Design and pilot test data collection tools
4. Collect baseline data before program starts
5. Track outcomes regularly using Outcomes Dashboard
6. Analyze data and create visualizations
7. Prepare Impact Report for stakeholders and funders

## Logic Model
LOGIC MODEL TEMPLATE
INSTRUCTIONS: Complete each section to show how your program creates change. Start with Impact (end goal) and work backwards.
INPUTS
Resources invested in the program
Examples: | Your Program:
Staff (FTE, roles)
Funding (sources, amounts)
Materials and supplies
Facilities and equipment
Partnerships and collaborations
Volunteer time
ACTIVITIES
What the program does
Examples: | Your Program:
Workshops and training sessions
One-on-one counseling
Group activities
Outreach and recruitment
Materials distribution
Follow-up and support
OUTPUTS
Direct products of activities (countable)
Examples: | Your Program:
# of participants served
# of workshops delivered
# of counseling sessions
# of materials distributed
# of volunteer hours
# of partnerships established
SHORT-TERM OUTCOMES
Immediate changes (0-6 months)
Examples: | Your Program:
Increased knowledge
Increased awareness
New skills acquired
Changed attitudes
Increased motivation
New connections made
INTERMEDIATE OUTCOMES
Medium-term changes (6-12 months)
Examples: | Your Program:
Changed behaviors
Applied new skills
Improved practices
Sustained engagement
Leadership development
System changes initiated
LONG-TERM OUTCOMES/IMPACT
Sustained changes (1+ years)
Examples: | Your Program:
Improved conditions
Changed status
Community-level changes
Policy changes
Systems transformation
Sustained impact
ASSUMPTIONS | EXTERNAL FACTORS
Beliefs about how program will work: | Conditions outside program control:

## Evaluation Plan
EVALUATION PLANNING WORKSHEET
INSTRUCTIONS: Define evaluation questions, methods, timeline, and responsibilities.
EVALUATION QUESTIONS
Question | Type | Method | Data Source | Timeline | Responsible | Budget
Are we reaching our target population? | Process | Survey | Participant records | Monthly | Program Mgr | $500
Are participants satisfied with program? | Process | Survey | Satisfaction survey | Quarterly | Evaluator | $1,000
Did participants gain knowledge? | Outcome | Pre-post test | Assessment | Pre/Post | Evaluator | $1,500
Did participants change behavior? | Outcome | Follow-up survey | 6-month survey | 6 months | Evaluator | $2,000
What is program completion rate? | Output | Records review | Database | Monthly | Program Mgr | $0
EVALUATION TIMELINE
Activity | Start Date | End Date | Status | Notes
Develop logic model | Month 1 | Month 1 | Complete
Create evaluation plan | Month 1 | Month 2 | In Progress
Design data collection tools | Month 2 | Month 2 | Not Started
Pilot test tools | Month 3 | Month 3 | Not Started
Collect baseline data | Month 3 | Month 3 | Not Started
Ongoing data collection | Month 4 | Month 12 | Not Started
Mid-point analysis | Month 6 | Month 6 | Not Started
Final data collection | Month 12 | Month 12 | Not Started
Data analysis | Month 12 | Month 13 | Not Started
Impact report | Month 13 | Month 13 | Not Started
EVALUATION BUDGET
Item | Cost | Notes
Evaluator/consultant fees | $5,000 | External evaluator
Survey tools/software | $1,000 | SurveyMonkey, Qualtrics
Incentives for participants | $500 | Gift cards for survey completion
Data analysis software | $500 | Excel, SPSS
Report design/printing | $500 | Professional report
TOTAL | $7,500

## Data Collection Tools
DATA COLLECTION TOOLS
INSTRUCTIONS: Use these templates to design surveys, interview guides, and observation protocols.
PARTICIPANT SATISFACTION SURVEY TEMPLATE
Program Name: _______________________ Date: _______________________ Please rate your experience with our program: 1. Overall, how satisfied are you with the program? ☐ Very Satisfied ☐ Satisfied ☐ Neutral ☐ Dissatisfied ☐ Very Dissatisfied 2. The program met my needs. ☐ Strongly Agree ☐ Agree ☐ Neutral ☐ Disagree ☐ Strongly Disagree 3. The staff were knowledgeable and helpful. ☐ Strongly Agree ☐ Agree ☐ Neutral ☐ Disagree ☐ Strongly Disagree 4. I would recommend this program to others. ☐ Strongly Agree ☐ Agree ☐ Neutral ☐ Disagree ☐ Strongly Disagree 5. What did you like most about the program? _________________________________________________________________ 6. What could be improved? _________________________________________________________________ 7. Additional comments: _________________________________________________________________
INTERVIEW GUIDE TEMPLATE
Participant Name: _______________________ Interview Date: _______________________ Interviewer: _______________________ INTRODUCTION: Thank you for agreeing to this interview. Your feedback will help us improve our program. This interview will take about 30 minutes. Your responses will be kept confidential. OPENING QUESTIONS: 1. Tell me about your experience with the program. 2. What motivated you to participate? PROGRAM EXPERIENCE: 3. What aspects of the program were most helpful to you? 4. What aspects were least helpful? 5. How has the program affected you? (knowledge, skills, behavior, etc.) OUTCOMES: 6. What changes have you noticed since participating? 7. Have you applied what you learned? How? 8. What barriers have you faced in applying what you learned? IMPROVEMENT: 9. What would you change about the program? 10. What additional support would be helpful? CLOSING: 11. Is there anything else you'd like to share? Thank you for your time and feedback!
OBSERVATION PROTOCOL TEMPLATE
Time | Activity Observed | Participant Engagement | Staff Actions | Notes

## Outcomes Tracking
OUTCOMES TRACKING DASHBOARD
INSTRUCTIONS: Track progress toward outcome targets. Update regularly with actual data.
Outcome | Indicator | Baseline | Target | Q1 | Q2 | Q3 | Q4
SHORT-TERM OUTCOMES
Increased knowledge | % scoring 80%+ on post-test | 45% | 70% | 52% | 58% | 65%
Increased awareness | % reporting increased awareness | 30% | 60% | 45% | 55% | 62%
New skills acquired | % demonstrating new skills | 20% | 50% | 35% | 42% | 48%
INTERMEDIATE OUTCOMES
Changed behaviors | % applying new behaviors | 10% | 40% | 15% | 25% | 35%
Improved practices | % using improved practices | 15% | 50% | 20% | 30% | 42%
Sustained engagement | % still engaged at 6 months | 50% | 75% | 55% | 62% | 70%
LONG-TERM OUTCOMES
Improved conditions | % reporting improved conditions | 5% | 30% |  |  | 12%
Changed status | % achieving status change | 10% | 25% |  |  | 15%
PROGRESS SUMMARY
Category | # Indicators | On Track | Behind | Ahead | % On Track
Short-term Outcomes | 3 | 2 | 1 | 0 | 67%
Intermediate Outcomes | 3 | 3 | 0 | 0 | 100%
Long-term Outcomes | 2 | 1 | 1 | 0 | 50%
TOTAL | 8 | 6 | 2 | 0 | 75%

## Data Analysis
DATA ANALYSIS TEMPLATES
INSTRUCTIONS: Use these templates to analyze quantitative and qualitative data.
QUANTITATIVE DATA ANALYSIS
Variable | N | Mean | Median | Min | Max
Pre-test score | 100 | 65 | 68 | 20 | 95
Post-test score | 100 | 82 | 85 | 45 | 100
Knowledge gain | 100 | 17 | 15 | -5 | 45
Satisfaction rating | 95 | 4.3 | 4.5 | 2.0 | 5.0
Program completion rate | 100 | 85% | 90% | 40% | 100%
PRE-POST COMPARISON
Measure | Pre | Post | Change | % Change | Significant?
Knowledge score | 65 | 82 | +17 | +26% | Yes
Confidence level | 3.2 | 4.1 | +0.9 | +28% | Yes
Skill demonstration | 45% | 78% | +33% | +73% | Yes
Behavior change | 20% | 55% | +35% | +175% | Yes
QUALITATIVE DATA ANALYSIS
Theme | # Mentions | % of Respondents | Example Quote
Program was helpful | 45 | 90% | This program changed my life
Staff were supportive | 38 | 76% | The staff really cared about my success
Learned practical skills | 42 | 84% | I use what I learned every day
Would recommend | 47 | 94% | Everyone should take this program
Need more time | 15 | 30% | I wish the program was longer
KEY FINDINGS SUMMARY
1. Participants showed significant knowledge gains (26% increase from pre to post)
2. Program completion rate (85%) exceeded target (80%)
3. Participant satisfaction was high (4.3/5.0)
4. 94% would recommend the program to others
5. Key themes: helpful program, supportive staff, practical skills
6. Area for improvement: 30% requested more program time

## Impact Report Template
IMPACT REPORT TEMPLATE
INSTRUCTIONS: Use this template to create your impact report. Customize for your audience.
EXECUTIVE SUMMARY
• Program overview (1-2 sentences)
• Key findings (3-5 bullets)
• Impact highlights (numbers + stories)
• Recommendations (2-3 items)
PROGRAM DESCRIPTION
• Program goals and objectives
• Target population
• Activities and services
• Logic model (reference)
EVALUATION APPROACH
• Evaluation questions
• Data collection methods
• Sample size and response rates
• Limitations
KEY FINDINGS
• Outputs (# served, # activities)
• Short-term outcomes (knowledge, skills)
• Intermediate outcomes (behavior change)
• Long-term outcomes (impact)
• Data visualizations (charts, graphs)
IMPACT STORIES
• Participant testimonials
• Case studies (2-3 examples)
• Before and after stories
• Photos (with permission)
LESSONS LEARNED
• What worked well
• What didn't work
• Unexpected findings
• Adaptations made
RECOMMENDATIONS
• Program improvements
• Scale-up opportunities
• Sustainability strategies
• Next steps
APPENDICES
• Data tables
• Survey instruments
• Interview guides
• Additional resources
IMPACT STORY TEMPLATE
Participant Name: [Use first name or pseudonym] BEFORE: [Describe situation before program] Example: "Maria was struggling to find employment after losing her job..." DURING: [Describe program participation] Example: "Through our job training program, Maria learned..." AFTER: [Describe outcomes and impact] Example: "Six months later, Maria secured a full-time position..." QUOTE: [Include participant quote] Example: "This program gave me the confidence and skills I needed to succeed." IMPACT: [Quantify impact when possible] Example: "Maria's income increased by 40% and she now mentors other participants."

## Continuous Improvement
CONTINUOUS IMPROVEMENT TRACKER
INSTRUCTIONS: Use PDSA cycles to test improvements. Track what works and what doesn't.
PLAN-DO-STUDY-ACT (PDSA) CYCLES
Cycle # | Problem/Opportunity | Plan (Change to Test) | Do (Implementation) | Study (Results) | Act (Next Steps) | Status
1 | Low survey response rate | Offer $10 gift card incentive | Tested with 50 participants | Response rate increased from 40% to 75% | Adopt for all surveys | Complete
2 | Participants missing sessions | Send reminder texts 24 hours before | Implemented for 1 month | Attendance improved from 70% to 85% | Continue and expand | Complete
3 | Low knowledge retention | Add practice exercises between sessions | Testing in next cohort | Results pending | TBD | In Progress
4 | [5 empty] | Not Started
IMPROVEMENT IDEAS LOG
Idea | Source | Priority | Resources Needed | Assigned To | Target Date | Status
Add peer mentoring component | Participant feedback | High | Mentor training | Program Mgr | Q2 | Planned
Create online resource library | Staff suggestion | Medium | $500 for platform | IT Staff | Q3 | Planned
Extend program by 2 weeks | Evaluation findings | High | Additional funding | Director | Q4 | Under Review
Partner with local employers | Advisory board | High | Staff time | Program Mgr | Q2 | In Progress
LESSONS LEARNED
Date | What Worked | What Didn't Work | Why | Action Taken
Q1 | Gift card incentives | Email reminders | Participants don't check email regularly | Switched to text reminders
Q2 | Small group activities | Large group lectures | Participants prefer interaction | Redesigned curriculum
Q3 | Flexible scheduling | Rigid attendance policy | Life happens - need flexibility | Revised policy